# Riverside Library Renovation Report

Prepared for Riverside Borough Council by the libraries team, October 2026.

# 1 Background

The Riverside Library opened in 1968 and last had a major refurbishment in 1994.

Visits fell from 212,000 in 2019 to 164,000 in 2025, while the number of registered members stayed close to 31,000.

The council approved the renovation on 14 March 2026 after a public consultation that drew 1,870 responses.

The building has three floors and a basement archive that holds the borough's local history collection of about 48,000 items, including parish maps, photographs and the minute books of the old harbour board.

Energy use in 2025 was 386 megawatt hours, about twice the figure for a modern library of the same size, mostly because of the single-glazed reading room windows and a gas boiler installed in 1981.

Opening hours were cut from 58 to 46 hours a week in 2023 to save staff costs. Saturday afternoons and Wednesday evenings were the sessions lost, and both were among the busiest before the cut.

# 2 Costs

Table 1 lists the main works packages, their contractors and when each is due to finish.

| Package | Contractor | Cost | Completion |
| --- | --- | --- | --- |
| Roof and insulation | Hartley Building Ltd | £1,240,000 | June 2027 |
| Lifts and ramps | Ascend Access | £385,000 | March 2027 |
| Children's library fit-out | Little Oak Interiors | £212,500 | September 2027 |
| Café and community room | Brookside Joinery | £178,000 | October 2027 |

A contingency of 10 per cent of the works cost is held by the council's capital programme board.

The total budget is £2.6 million, of which £1.1 million comes from a national library improvement grant and the rest from the council's own capital programme.

## 2.1 North wing

Temporary closure starts on 1 February 2027 and lasts eleven weeks.

Staff move to the mobile library van during the works.

Returned books are collected at the leisure centre reception.

## 2.2 South wing

Temporary closure starts on 6 September 2027 and lasts seven weeks.

Staff move to the town hall annexe during the works.

Returned books are collected at the Mill Lane post office.

# 3 Risks

Asbestos was found in the boiler room ceiling during the March 2026 survey; removal is priced at £46,000.

A bat roost under the east eaves may delay the roof works until the end of the breeding season.

The children's library stays open throughout, using the side entrance on Wharf Street.

Steel prices could add up to £90,000 to the roof package if the tender slips past January, because the contractor's quotation is only held for ninety days.

# 4 Programme

Works start on 4 January 2027 with the roof, which must be watertight before the lifts are installed. The main contractor's site compound will take half of the staff car park until December 2027.

Progress meetings are held every Tuesday at the council offices, and a public update is posted on the library noticeboard and the council website on the first Monday of each month.

The local history archive is packed and moved to the county record office for the whole programme; researchers can book visits there on Thursdays.

# 5 Consultation findings

The most requested change was longer opening hours, named by 62 per cent of respondents. Quiet study space came second, and free Wi-Fi that works on every floor came third.

Parents asked for a buggy park and a baby-changing room on the ground floor; both are now in the design. Older residents asked to keep the large-print section on the ground floor, near the entrance.

Fewer than 1 in 10 respondents asked for a café. It was kept because its rent will pay the running costs of the community room, which local groups can then book for free.

# 6 Accessibility

The new lift serves all three floors and the basement, with a car large enough for a wheelchair user and a companion. Hearing loops will be fitted at the help desk, in the community room and in the children's library.

Two accessible toilets replace the single one on the first floor, and the front steps get a handrail on both sides and a ramp at a gradient of 1 in 15.

# 7 Next steps

The cabinet will be asked to release the second half of the budget at its meeting on 12 November 2026. A temporary library manager will be appointed for the closure periods, paid from the contingency.

Visit counts come from the door sensors installed in 2017, which miss visitors who arrive with school groups.

The works cost excludes VAT, which the council recovers in full.

Survey by Northfield Environmental, report NE-2291, dated 18 March 2026.